## Template
IMPLEMENTATION TRACKER TEMPLATE | [11 empty] | ▣ Kulic Advisory Template
From agreed actions to controlled execution
⚙ PROGRAM [Program / Workstream] |  |  |  | ◎ IMPLEMENTATION LEAD [Name / Role] |  |  |  | ▣ SCOPE [Entities / Countries / Functions] |  |  |  | ▤ REPORTING DATE [DD MMM YYYY]
1. EXECUTION CONTROL DASHBOARD
OPEN ACTIONS =COUNTIF(N18:N57,"<>Complete") |  |  | OVERDUE =COUNTIF(P18:P57,"Overdue") |  |  | HIGH PRIORITY =COUNTIF(M18:M57,"High")+COUNTIF(M18:M57,"Critical") |  |  | DECISIONS NEEDED =COUNTIF(L18:L57,"Yes") |  |  | COMPLETION =IFERROR(COUNTIF(N18:N57,"Complete")/COUNTA(N18:N57),0)
2. IMPLEMENTATION ACTION TRACKER
# | Phase | Workstream | Action / Deliverable | Description | Owner | Support | Start | Due Date | Dependency | Risk / Blocker | Decision Needed | Priority | Status | Progress % | Health
1 | Design | [Workstream] | [Action 1] | [Short description] | [Owner] | [Support] | [Start] | [Due] | [Dependency] | [Risk / blocker] | No | Medium | Planned | 6.667%
2 | Build | [Workstream] | [Action 2] | [Short description] | [Owner] | [Support] | [Start] | [Due] | [Dependency] | [Risk / blocker] | No | Medium | In Progress | 13.33%
3 | Test | [Workstream] | [Action 3] | [Short description] | [Owner] | [Support] | [Start] | [Due] | [Dependency] | [Risk / blocker] | No | Medium | Blocked | 20%
4 | Deploy | [Workstream] | [Action 4] | [Short description] | [Owner] | [Support] | [Start] | [Due] | [Dependency] | [Risk / blocker] | No | High | Complete | 26.67%
5 | Stabilize | [Workstream] | [Action 5] | [Short description] | [Owner] | [Support] | [Start] | [Due] | [Dependency] | [Risk / blocker] | No | Medium | Not Started | 33.33%
6 | Discover | [Workstream] | [Action 6] | [Short description] | [Owner] | [Support] | [Start] | [Due] | [Dependency] | [Risk / blocker] | Yes | Medium | Planned | 40%
7 | Design | [Workstream] | [Action 7] | [Short description] | [Owner] | [Support] | [Start] | [Due] | [Dependency] | [Risk / blocker] | No | Medium | In Progress | 46.67%
8 | Build | [Workstream] | [Action 8] | [Short description] | [Owner] | [Support] | [Start] | [Due] | [Dependency] | [Risk / blocker] | No | High | Blocked | 53.33%
9 | Test | [Workstream] | [Action 9] | [Short description] | [Owner] | [Support] | [Start] | [Due] | [Dependency] | [Risk / blocker] | No | Medium | Complete | 60%
10 | Deploy | [Workstream] | [Action 10] | [Short description] | [Owner] | [Support] | [Start] | [Due] | [Dependency] | [Risk / blocker] | No | Medium | Not Started | 66.67%
11 | Stabilize | [Workstream] | [Action 11] | [Short description] | [Owner] | [Support] | [Start] | [Due] | [Dependency] | [Risk / blocker] | No | Medium | Planned | 73.33%
12 | Discover | [Workstream] | [Action 12] | [Short description] | [Owner] | [Support] | [Start] | [Due] | [Dependency] | [Risk / blocker] | Yes | High | In Progress | 80%
13 | Design | [Workstream] | [Action 13] | [Short description] | [Owner] | [Support] | [Start] | [Due] | [Dependency] | [Risk / blocker] | No | Medium | Blocked | 86.67%
14 | Build | [Workstream] | [Action 14] | [Short description] | [Owner] | [Support] | [Start] | [Due] | [Dependency] | [Risk / blocker] | No | Medium | Complete | 93.33%
15 | Test | [Workstream] | [Action 15] | [Short description] | [Owner] | [Support] | [Start] | [Due] | [Dependency] | [Risk / blocker] | No | Medium | Not Started | 100%
3. ESCALATION LOG | [8 empty] | 4. NEXT 7 DAYS
Issue | Impact | Escalated To | Decision Required | Due Date | Status |  |  |  | Focus Area | Action | Owner | By When
[Blocker] | [Impact on scope/timeline/value] | [Sponsor] | [Decision] | [DD MMM YYYY] | Open |  |  |  | [Critical path] | [Action] | [Owner] | [Date]
[Dependency] | [Impact on scope/timeline/value] | [Sponsor] | [Decision] | [DD MMM YYYY] | Open |  |  |  | [Decision] | [Action] | [Owner] | [Date]
[9 empty] | [Risk] | [Action] | [Owner] | [Date]
◇ K U L I C A D V I S O R Y https://www.kulicadvisory.com ¦ @KulicAdvisory
Formulas:
Health = IF(AND([Status]<>"Complete",[Due Date]<TODAY()),"Overdue",IF([Status]="Blocked","Blocked","OK"))

## Instructions
Implementation Tracker Template
Purpose | Track actions, blockers, decisions and implementation health without turning the tracker into a spreadsheet jungle.
How to use | 1. Replace bracketed placeholders with your own data. 2. Use dropdowns for Status, Priority, RAG, Phase, Role and Score where provided. 3. Use formula fields as calculation areas, not as static text. 4. Keep client-specific data out before publishing externally. 5. Export to PDF for presentation, or keep XLSX editable for client work.
Source inspiration | Inspired by uploaded implementation tracker. Simplified to a reusable execution-control template with clearer ownership, priority and escalation logic.
Branding | Kulic Advisory & Consulting. Website-ready template asset. Footer includes https://www.kulicadvisory.com and @KulicAdvisory.

## Lists (hidden)
Status | Priority | RAG | Phase | Score | RASCI | Risk | YesNo
Not Started | Low | Green | Discover | 1 | R | Low | Yes
Planned | Medium | Amber | Design | 2 | A | Medium | No
In Progress | High | Red | Build | 3 | S | High | TBC
Blocked | Critical |  | Test | 4 | C | Critical
At Risk |  |  | Deploy | 5 | I
Complete |  |  | Stabilize
On Hold |  |  | Sustain