## Template
CROSS-FUNCTIONAL ACTION LOG TEMPLATE | [11 empty] | ▣ Kulic Advisory Template
CFT actions, owners, due dates, blockers and escalation
☷ CATEGORY / TOPIC [Category / Workstream] |  |  |  | ◎ MEETING FORUM [CFT / SteerCo / Workstream] |  |  |  | ▤ MEETING DATE [DD MMM YYYY] |  |  |  | ⚑ ACTION LOG OWNER [Name / Role]
1. ACTION LOG DASHBOARD
OPEN =COUNTIF(N18:N77,"Open") |  |  | OVERDUE =COUNTIF(P18:P77,"Overdue") |  |  | DUE THIS WEEK =COUNTIFS(I18:I77,">="&TODAY(),I18:I77,"<="&TODAY()+7,N18:N77,"<>Closed") |  |  | ESCALATIONS =COUNTIF(L18:L77,"Yes") |  |  | CLOSED =COUNTIF(N18:N77,"Closed")
2. MEETING ACTION LOG
# | Category | Meeting / Forum | Description | Owner | Support | Assignment Date | Original Due Date | Revised Due Date | Comments | Decision Needed | Escalation? | Priority | Status | Next Step | Health
1 | [Category] | CFT | [Action 1] | [Owner] | [Support] | [Assigned] | [Due] | [Revised Due] | [Comment] | No | No | Medium | In Progress | [Next step]
2 | [Category] | CFT | [Action 2] | [Owner] | [Support] | [Assigned] | [Due] | [Revised Due] | [Comment] | No | No | Medium | Closed | [Next step]
3 | [Category] | CFT | [Action 3] | [Owner] | [Support] | [Assigned] | [Due] | [Revised Due] | [Comment] | No | No | Medium | Blocked | [Next step]
4 | [Category] | CFT | [Action 4] | [Owner] | [Support] | [Assigned] | [Due] | [Revised Due] | [Comment] | No | No | High | Open | [Next step]
5 | [Category] | CFT | [Action 5] | [Owner] | [Support] | [Assigned] | [Due] | [Revised Due] | [Comment] | Yes | No | Medium | In Progress | [Next step]
6 | [Category] | CFT | [Action 6] | [Owner] | [Support] | [Assigned] | [Due] | [Revised Due] | [Comment] | No | No | Medium | Closed | [Next step]
7 | [Category] | CFT | [Action 7] | [Owner] | [Support] | [Assigned] | [Due] | [Revised Due] | [Comment] | No | Yes | Medium | Blocked | [Next step]
8 | [Category] | CFT | [Action 8] | [Owner] | [Support] | [Assigned] | [Due] | [Revised Due] | [Comment] | No | No | High | Open | [Next step]
9 | [Category] | CFT | [Action 9] | [Owner] | [Support] | [Assigned] | [Due] | [Revised Due] | [Comment] | No | No | Medium | In Progress | [Next step]
10 | [Category] | CFT | [Action 10] | [Owner] | [Support] | [Assigned] | [Due] | [Revised Due] | [Comment] | Yes | No | Medium | Closed | [Next step]
11 | [Category] | CFT | [Action 11] | [Owner] | [Support] | [Assigned] | [Due] | [Revised Due] | [Comment] | No | No | Medium | Blocked | [Next step]
12 | [Category] | CFT | [Action 12] | [Owner] | [Support] | [Assigned] | [Due] | [Revised Due] | [Comment] | No | No | High | Open | [Next step]
13 | [Category] | CFT | [Action 13] | [Owner] | [Support] | [Assigned] | [Due] | [Revised Due] | [Comment] | No | No | Medium | In Progress | [Next step]
14 | [Category] | CFT | [Action 14] | [Owner] | [Support] | [Assigned] | [Due] | [Revised Due] | [Comment] | No | Yes | Medium | Closed | [Next step]
15 | [Category] | CFT | [Action 15] | [Owner] | [Support] | [Assigned] | [Due] | [Revised Due] | [Comment] | Yes | No | Medium | Blocked | [Next step]
16 | [Category] | CFT | [Action 16] | [Owner] | [Support] | [Assigned] | [Due] | [Revised Due] | [Comment] | No | No | High | Open | [Next step]
17 | [Category] | CFT | [Action 17] | [Owner] | [Support] | [Assigned] | [Due] | [Revised Due] | [Comment] | No | No | Medium | In Progress | [Next step]
18 | [Category] | CFT | [Action 18] | [Owner] | [Support] | [Assigned] | [Due] | [Revised Due] | [Comment] | No | No | Medium | Closed | [Next step]
19 | [Category] | CFT | [Action 19] | [Owner] | [Support] | [Assigned] | [Due] | [Revised Due] | [Comment] | No | No | Medium | Blocked | [Next step]
20 | [Category] | CFT | [Action 20] | [Owner] | [Support] | [Assigned] | [Due] | [Revised Due] | [Comment] | Yes | No | High | Open | [Next step]
3. DECISION / ESCALATION REGISTER | [8 empty] | 4. MEETING DISCIPLINE
Escalation | Reason | Decision Owner | Requested Decision | Required By | Status |  |  |  | One action = one accountable owner.
[Escalation 1] | [Risk / dependency] | [Owner] | [Decision] | [Date] | Open |  |  |  | Every revised date requires a reason.
[Escalation 2] | [Risk / dependency] | [Owner] | [Decision] | [Date] | Open |  |  |  | No owner means no action.
Escalation is a control mechanism, not a failure.
◇ K U L I C A D V I S O R Y https://www.kulicadvisory.com ¦ @KulicAdvisory
Formulas:
Health = IF(AND([Status]<>"Closed",[Revised Due Date]<TODAY()),"Overdue",IF([Status]="Blocked","Blocked","OK"))

## Instructions
Cross-Functional Action Log Template
Purpose | Track CFT meeting actions in a clean, accountable way with due dates, escalations and health logic.
How to use | 1. Replace bracketed placeholders with your own data. 2. Use dropdowns for Status, Priority, RAG, Phase, Role and Score where provided. 3. Use formula fields as calculation areas, not as static text. 4. Keep client-specific data out before publishing externally. 5. Export to PDF for presentation, or keep XLSX editable for client work.
Source inspiration | Inspired by uploaded CFT action log. Simplified to remove noise and make ownership, due dates and escalation visible.
Branding | Kulic Advisory & Consulting. Website-ready template asset. Footer includes https://www.kulicadvisory.com and @KulicAdvisory.

## Lists (hidden)
Status | Priority | RAG | Phase | Score | RASCI | Risk | YesNo
Not Started | Low | Green | Discover | 1 | R | Low | Yes
Planned | Medium | Amber | Design | 2 | A | Medium | No
In Progress | High | Red | Build | 3 | S | High | TBC
Blocked | Critical |  | Test | 4 | C | Critical
At Risk |  |  | Deploy | 5 | I
Complete |  |  | Stabilize
On Hold |  |  | Sustain